## Slide 1: Utilising Tools and Technology to Optimise Project Management - A Case Study
Mark LOANEY
Project Development Excellence for the Public Sector
Notes: Abstract: If you intend to move towards greater precision on cost based project planning, there are many tools available to capture the necessary information and track the information most relevant to your projects. Although software itself does not make project managers effective, it can improve efficiency by providing the necessary controls and mechanisms to manage your projects. This paper and presentation covers practical experience gained by the author in the implementation of cost based project management and leveraging off this to improve estimating for future projects. Experience at several large councils in NSW and with City Design at Brisbane City Council will be drawn upon to outline a methodology and the processes used in managing projects. Whilst there have been a proliferation of tools in recent years, this paper focuses on the use of a custom built applications that utilises Microsoft Project and Access.

## Slide 2: Overview
History
  Introduction to Cost Recovery (Dubbo)
  Extending to Incorporate Inputs & Outputs (Fairfield)
  Tracking Resource Utilisation (City Design, Brisbane)
The Project Cycle
  Bidding
  Project Creation
  Resource Allocation
  Tracking Actuals
  Invoicing & Reporting
Conclusions
  Working smarter, not harder
  Realising Benefits
Notes: Overview
The presentation that will be given today focuses on the use of the Cost Control System Developed by OranaSoft and it’s use in the tracking of costs and managing projects within a service delivery organisation, ie a Design Consultancy Group. Discussion will outline why typical financial systems are not adequate to assist the Project Manager.
The following items will be discussed in this presentation:
1. History
1.1. The introduction of cost recovery at Dubbo City Council
1.2. Extension to include inputs & outputs Bankstown / Fairfield Councils
1.3. Addition of Resource Tracking City Design, Brisbane City Council
2. The Project Cycle
2.1. Bidding
2.2. Project Registration & Creation
2.3. Resource Allocation
2.4. Task Definition & Progress Reporting
2.5. Tracking Actuals (performing the work)
2.6. Document Management
2.7. Invoicing
2.8. Reporting
3. Conclusions
3.1. Benefits Realised
Working smarter, not harder

## Slide 3: Cost Recovery
March 1995 - decision to implement cost recovery in TSB
No system readily available, wrote own!
June 1995 - Live trial of version 1 of Cost Control System
July 1995 - Full implementation of system
Notes: 1.1 History of Cost Recovery at Dubbo City Council (Manager Technical Support)
In March 1995 the Executive at Dubbo City Council decided we should take the first steps in implementing full cost recovery, with implementation in July 1995. The Technical Support Branch was chosen to trial it’s introduction. At that stage there was no system or methodology in place to implement this decision.
By June 1995, I had developed a cost recovery system using Microsoft Access V2 to record details of all projects undertaken electronically including details of times spent by each employee on specific projects. A trial run of the system was undertaken this month with all team members using the system.
July 1995 saw full implementation of the system at with all team members recording actual times worked against specific projects from within the system. The system was also used to generate agreed briefs between the Branch and potential clients.
During early August 1997, I decided to set up my own software development company (OranaSoft) and commenced work on developing a new system that could be used by any business unit within any organisation. This system was written in Microsoft Access 97 and after completion in January 1998 was implemented at Dubbo City Council in February 1998.

## Slide 4: Inputs & Outputs
New users, new requirements
Activity based inputs
KPI’s determined based on outputs
Notes: 1.2 Inputs & Outputs (Bankstown, Fairfield, Griffith)
The system gained acceptance in Dubbo, with other Council’s expressing an interest in implementing project management software to track actual costs and time on projects. By October 1999, three other councils had joined Dubbo in using this system.
With these additional users, the capabilities of the system were stretched. The need to capture specific inputs (activities that contribute to performing a project) and outputs (the actual deliverables), in terms of estimated and actual was required

## Slide 5: Resource Tracking
City Design, Brisbane City Council – need to determine workloads across 50 contractors, employees
Required integration with MS Project
Resource pooling in Project not working.
Notes: 1.3 Resource Tracking (Water & Environment, City Design, Brisbane City Council)
Moving to City Design within the Brisbane City Council brought additional challenges. It simply was not practical to capture only time and cost information in terms of actual. Forward planning to develop resourcing levels across the Water & Environment Group was needed to determine workloads for the 50 staff and contractors working in the group.
The Design group already had it’s own implemented timesheet and costing system, hence the development of the project management system had the goal of integrating already available systems and extending their capabilities to capture the required information. Thus by December 2000, the system that started out as a time tracking and costing tool had developed into a fully functional project management system, integrating with other third party systems and Microsoft tools (Project, Word, Internet Explorer).

## Slide 6: Focus – The Project Cycle
Focus on Service Provider
Financial systems are for accountants
Technology Integration
Other Systems not covered in this presentation
Notes: In this section of the paper, the focus is on the utilisation of technology to assist the project manager in effectively performing that role. The focus will be on the use of the systems briefly outlined earlier and how they are being used in a service provision organisation. Whilst there are other systems available that perform the same or similar tasks, they will not be covered in any detail in this presentation, rather a summary of these systems will be provided at the end of the paper.
It is important to highlight the fact that Financial Systems are not Project Management Systems. I have come across many instances where accountants have tried to make the financial system the tool of choice for tracking actual costs in projects. However, with their focus being on charts of accounts and tracking costs against cost centres, they do not provide the detailed information that the modern project manager requires to effectively manage their projects. Some of the shortcomings include
an inability to report on actual people used on a project on a time and cost basis, summarising this information;
a sparsity of graphing and reporting tools to indicate exception

## Slide 7: Project Management Process

## Slide 8: Main Menu

## Slide 9: Proposal Preparation - Bidding
Winning the next project
  Compiling available information
  Assigning Bid Manager
  Setting Deadlines
  QA Procedures
  Reviews
  Hitting the deadline

## Slide 10: Bid Manager

## Slide 11: Detailed information recorded

## Slide 12: Detailed information recorded

## Slide 13: Detailed information recorded

## Slide 14: Detailed information recorded

## Slide 15: Project Management Process

## Slide 16: Project Creation
Critical
  Define and agree on scope
    Use fixed fee when scope clear
    Do & Charge for ‘fuzzy’ objectives, and
    Annual for ongoing and non recoverable projects
  Prepare brief, set fee and agree on dates

## Slide 17: Project Creation (Master)

## Slide 18: Project Creation (Inputs)

## Slide 19: Project Creation (Outputs)

## Slide 20: Project Creation (Time Phasing)

## Slide 21: Project Management Process

## Slide 22: Assigning Resources
In order to keep track of who is available for new projects and who is already allocated, resources need to be assigned
CPM
  Integrates with MS Project
  Provides a 4 week window into resource allocations
  Enables a review of allocations on a by project basis
  Produces a 14 week allocation report

## Slide 23: MS Project Setup
Develop Gantt Chart
  Identify Tasks
  Assign Resources

## Slide 24: Resources
Important to set up resources in terms of people to use as a base for all projects
We use officer codes as the link to CPM

## Slide 25: Data Mapping
MS Project utilises a powerful data mapping wizard that enables you to assign fields in Project that match those in your Access Database

## Slide 26: Exporting From Project
MS Project has VBA embedded within
Programming incorporated to import and export data between Access and Project

## Slide 27: Resource Management Form

## Slide 28: Project Manager Review

## Slide 29: Employee Allocations

## Slide 30: Group Allocation Matrix

## Slide 31: Overview - Project & Resources

## Slide 32: Project Management Process

## Slide 33: Task Definition
Assign resources to tasks
Imported from MS Project
CPM allows users to view tasks across all projects, or by project
Tasks can be tracked to keep record of actions taken, meetings held etc
Memo’s can be produced to provide comprehensive feedback to clients

## Slide 34: Adding Tasks

## Slide 35: Managing Tasks

## Slide 36: Progress Reporting

## Slide 37: Project Management Process

## Slide 38: Project Team Working
Team clear on requirements and responsibilities
Record actual times worked
Allocate times to projects
Print timesheets
History of recoverable / non recoverable

## Slide 39: Time / Cost Sheet

## Slide 40: Keeping on Track

## Slide 41: Flex Sheet

## Slide 42: Project Management Process

## Slide 43: Tracking Costs

## Slide 44: Viewing Progress / Work

## Slide 45: Assigning Actuals
Need means of defining actual quantities used in the development of the project
Including:
  Times worked
  Plant used
  Actual inputs (sub-components)
  Actual Outputs

## Slide 46: Screen Shots

## Slide 47: Project Management Process

## Slide 48: Document Management
Digital documents provides linkages to files stored on your system
Issue management stores issues associated with the project categorised by type
Conversation record can store e-mails, verbal conversations and an overview of memos, reports etc received

## Slide 49: Document Management Screen

## Slide 50: Issue Management

## Slide 51: Record of Conversation

## Slide 52: Project Management Process

## Slide 53: Preparing Invoices
Manages information required to prepare and send invoice
Checks for missing information
Tracks which invoices have been sent
Grouped or on individual project basis
Handles internal journal preparation
Invoices can be deferred or delayed

## Slide 54: Accounts & Billing

## Slide 55: Invoice Module

## Slide 56: Sample Invoice

## Slide 57: Reporting
78 Reports
Logically grouped
Customisable
Filtered

## Slide 58: The Next Project

## Slide 59: Other Systems out there
Microsoft Project – few projects, few resources
Search the web, but includes
  Primavera
  Advanced Management Solutions
  Time Disciple
Accounting Systems are not Project Management Systems!

## Slide 60: Conclusions
Project Management Software can improve:
  Estimating – new based on historical
  Control – information at your fingertips
  Confidence – in how work is tracking, as well as ability to deliver consistently
  Accountability – times as well as costs are tracked

## Slide 61: Conclusions - 2
Essential
  Devolve data entry
  Exception reporting to assess currency

## Slide 62: Questions
Visit OranaSoft on the web @
www.oranasoft.com.au